MAK VARSITY AWARDS 2015 WORK PLAN

| PHASE ONE |  |
| --- | --- |
| Consultations, Event Review | April |
| Proposal Writing | May |
| Submission of proposals to sponsors/ partners | June |
| Finalising Submission of the proposals | July |
| PHASE TWO |  |
| Meetings with Sponsors, Partners/Follow ups | July-August |
| UNVEILING OF THE PROJECT/PRESS BRIEFING/PRESS INTERVIEWS | 23rd September |
| NOMINATION PROCESS | 23rd - 30th September |
| NOMINATION NIGHT (premiering nominees) at Freedom Square | 2nd October |
| VOTING | 3rd -13th October |
| AWARDS DAY( MAKERERE MAIN HALL) | 15th October |
| MAK VARSITY AWARD WINNER’S, PARTNERS AND SPONSORS DINNER | 24th October. |